## Project Settings
/Proyecto/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Project Settings
Project Owner | Kevin Ray Marzola Otero
Start Date | mar 18, 2017 06:01:42 PM
Completion Date | mar 19, 2017 11:02:37 PM | Completed: *
Keywords
Language | Java
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:22 PM el 21/03/2017

## Overall Metrics
/Proyecto/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 41 | 13.8 | 38.6
Planned Time | 0.12222 |  | 1899-12-31 03:33
Actual Tiempo |  | 0.12708 | 0.98333
CPI (Cost-Performance Index) |  |  | 1.17
% Reuse | 0% | 0% | 7.56%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 4.6 | 0 | 4.39
Total Defects/KLOC or equivalent | 15 | 23.8 | 15.4
Yield % | 100% | 100% | 100%
Code Review Rate | 683 | 360 | 675
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:23 PM el 21/03/2017

## Program Size
/Proyecto/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 145 | 145 | 317
Deleted (D) | 6 | 11 | 66
Modified (M) | 12 | 12 | 37
Added (A) | 108 | 30 | 874
Reused (R) | 0 | 0 | 74
Added and Modified (A+M) | 120 | 42 | 911
Total Size (T) | 247 | 164 | 979
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 130 | 147 | 723
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:24 PM el 21/03/2017

## Time In Phase
/Proyecto/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.024306 | 0.058333 | 0.22917 | 23.3%
DiseÃ±o | 0.013194 | 0.00625 | 0.097222 | 9.89%
RevisiÃ³n de DiseÃ±o | 0.0076389 | 0.013889 | 0.069444 | 7.06%
CodificaciÃ³n | 0.047222 | 0.021528 | 0.35139 | 35.7%
RevisiÃ³n de CodificaciÃ³n | 0.0076389 | 0.0048611 | 0.05625 | 5.72%
CompilaciÃ³n | 0.0041667 | 0 | 0.029861 | 3.04%
Pruebas | 0.00625 | 0.0034722 | 0.046528 | 4.73%
Postmortem | 0.011806 | 0.01875 | 0.10347 | 10.5%
Total | 0.12222 | 0.12708 | 0.98333
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:24 PM el 21/03/2017

## Defects Injected
/Proyecto/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0.28 | 0 | 2 | 14.3%
DiseÃ±o | 0.83 | 0 | 6 | 42.9%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 0.14 | 1 | 2 | 14.3%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.55 | 0 | 4 | 28.6%
Total | 1.8 | 1 | 14
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:25 PM el 21/03/2017

## Defects Removed
/Proyecto/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.28 | 0 | 2 | 14.3%
DiseÃ±o | 0.14 | 0 | 1 | 7.14%
RevisiÃ³n de DiseÃ±o | 0.28 | 0 | 2 | 14.3%
CodificaciÃ³n | 0.42 | 0 | 3 | 21.4%
RevisiÃ³n de CodificaciÃ³n | 0.14 | 1 | 2 | 14.3%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.55 | 0 | 4 | 28.6%
Total | 1.8 | 1 | 14
After Development | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:25 PM el 21/03/2017

## Defect Removal Efficiency
/Proyecto/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 1.45 | 0 | 1.2
Defects/Hour - Code Review | 0.79 | 8.57 | 1.48
Defects/Hour - Compile | 0 | #DIV/0! | 0
Defects/Hour - Test | 3.75 | 0 | 3.58
DRL (DLDR/UT) | 0.39 | 0 | 0.33
DRL (Code Review/UT) | 0.21 | 2.39 | 0.41
DRL (Compile/UT) | 0 | #DIV/0! | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:26 PM el 21/03/2017